## DoD
Definition of done
All code should be peer reviewed
All features should be accepted by the PO
All accepted features should be user tested
Code must be intuitive to read
Version control should be incorporated

## Product Backlog
Product backlog
Items | MoSCoW | Legend:
A database which can hold information about students, classes and teachers. | M |  | neutral/ nothing
A login service which works in both an app and a website/application. | M
A search function to look through the content of the database. | M
A mobile application for students. | M
A desktop application for teachers. | M
User permissions for both students and teachers. | M
A fail safe for when a teacher needs to be replaced (access to right classes). | M
Options to sort the data from the database by name, class etc. | M
An option to allow for the creating of a super user which can edit the whole system (admin) | M
Schedule free hours should not put students to absent | M
The teachers should be able to check off the attendance of their students | M
A page with advanced statistics that for instance, calculate percentage of attendance in certain lectures. (?) | M
An option to allow more than one super user | S
Options to fix mistakes made by teachers (undo/delete buttons) | S
Functionality that prompts the user to take a selfie after they've logged in for the first time. | S
An option to notify teachers about absence beforehand for students. | C
An option for teachers to make notes about certain students. | C
A Mobile application for teachers. | C

## Sprint 1
Sprint backlog 1
Userstory | Tasks | Acceptance criteria | Workload
As a developer I need to obtain more knowledge about databases | Gain more knowledge about postgres | We are able to work with sql, create databases, input data, retrieve data.
As a developer I need to decide what technologies I am going to use. | Gain knowledge about languages and frameworks and decide which we are going to use for this project | We have decided the technologies we are going to use and are ready to work with them.
As a developer I need to get familiar again with android studio. | Regain familiarity with android studio and developing an app | We are ready to start working with android studio.
As a developer I need to gain knowledge from my stakeholders | Use a form to inquire about the necessities the stakeholders want | Teachers actually answered the google form

## Retrospective 1
Bastiaan | Caglar | Daan | Damian | Delano
What went well | What went well | What went well | What went well | What went well
Why did it go well | Why did it go well | Why did it go well | Why did it go well | Why did it go well
What could have been better | What could have been better | What could have been better | What could have been better | What could have been better
Improvable | Improvable | Improvable | Improvable | Improvable

## Review 1
What went well | Why it went well | Barriers | Possible solution